Strachur Primary and Pre 5 Unit

Contents:

- Overview of Establishment 3 Year Cycle of Improvement Plan Priorities

- Strategic Improvement  Planning for Establishment

- Operational Improvement Planning (Action Plan) for Establishment

- Establishment Maintenance Improvement Planning

- Pupil Equity Fund Planning

| Overview of Establishment 3 Year Cycle of Improvement Plan Priorities |  |  |  |  | Session: 2025-2026 |
| --- | --- | --- | --- | --- | --- |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. - High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  |  |  |  |
| National Improvement Priorities | HGIOS 4 |  | Early Learning and Childcare Quality Indicators |  | Argyll and Bute Education Key Priorities |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/ securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning |  | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress - Safeguarding and child protection |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |
| Strategic Priorities 3 Year Cycle |  |  |  |  |  |
| 2025 – 2026: |  | 2026 – 2027: |  | 2027 – 2028: |  |
| Continue to raise attainment in Literacy and Numeracy Improve attendance cross school. Continue to improve Health & Wellbeing of learners across school and Pre-5 Continue to progress towards RRS Gold journey OCTNE accreditation journey |  | Improve Attainment and Achievement RRS gold award achieved Improve Health & Wellbeing of learners across school and Pre-5 OCTNE Silver accreditation |  | Improve Attainment and Achievement Improve Health & Wellbeing of learners across school and Pre-5 OCTNE Gold accreditation |  |

| Strategic Improvement Planning for Establishment: Overview of Links to Key Policies |  |  |  | Session: 2025-2026 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. - High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  |  | Collaboration and Consultation |  |  |
|  |  |  |  | Who? | When? | How? |
|  |  |  |  | Pupils | Ongoing | Assemblies, surveys, questionnaires, Pupil council |
|  |  |  |  | Staff | Termly | Curriculum Bulletins, self-evaluation, meetings |
|  |  |  |  | Families | Termly | Questionnaires, Parent council, attendance at learning workshops |
| National Improvement Framework Priorities | HGIOS 4 | Early Learning and Childcare Quality Indicators |  | Argyll and Bute Education Key Objectives |  |  |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/Securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress - Safeguarding and child protection |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |  |  |
| Priorities | Proposed Outcome and Impact |  | Measures |  |  | Linked to PEF (Y/N) |
| Priority 1 Improving Attainment and Attendance - Q.I. Approach to Writing - Written Presentation Skills - Numeracy Interventions - Support for Learning Paperwork - Parental Learning Workshops - Attendance Monitor weekly attendance reports to ensure children are attending school in line with local authority targets or above. Priority 2 Improving Health & Wellbeing - Our Children, Their Nurturing Education (OCTNE) Priority 3 Parental Engagement and Pupil Empowerment - Improving Outdoor Spaces for Primary & Pre-5 Learners - Parental Literacy, Numeracy and Health & Wellbeing Focus workshops - Social Media - Pupil Empowerment | Principal Teacher will complete training at Cohort 8 of Argyll & Bute training for QI Writing Impact: Improved attainment in Writing across school. Expectations for presentation of written work will be developed and regularly shared with learners. Learners’ written work will be regularly moderated to ensure improvement and next steps to progress. Impact: Improved written presentation across whole school. Impact: Presentation of written work will be shared, understood and improved upon for 95% of learners. Numeracy interventions (Catch-up Numeracy, 5 Min box, Power of 2) will be timetabled for identified learners alongside ongoing assessments to identify gaps in learning and plan for next steps. Impact: By June 2026 school ACEL Data for Numeracy will have improved by 5% to 83% in line with authority stretch aim for 2025/26 Strategy Sheets detailing learning support for identified individuals will be developed and shared with parents. Impact: 100% of parents of those learners targeted for Numeracy interventions, will be aware of the support offered to their child and discuss Strategy Sheet put in place to record support. Parental Learning workshops will be offered across session to support learning at home. Impact: Whole school XBRA Data for June 2026 for Numeracy will increase by a minimum of 2% and be in line with Stretch Aim of 85%. School will have a clear, shared routine for supporting improved attendance with supports in place for children and families. Impact: By 31st May 2026 school attendance data will demonstrate an increase to 94.5% from a baseline (31st May 2025) of 91.26% A range of data will be collected to support Health and Wellbeing of all learners. Impact: School will have range of data to support Health & Wellbeing of learners and their families. Attendance data will improve by 3.25% from 91.25 as at June 2025 to 94.50 as of June 2026. Outdoor areas across school and Pre-5 will be enhanced to incorporate a range of materials, activities and opportunities for active play and learning. Impact: By June 2026 outdoor spaces across Strachur Primary and Pre-5 will have at least one improvement as verbally reported by learners, Parent Council and Pupil Council. A clear calendar of Parental Engagement offers for all classes (inc Pre-5) across the academic year will be shared via Aug – Oct Newsletter. Impact: By June 2026 100% of parents will have been invited to participate in Literacy, Numeracy and Health & Wellbeing workshops. A range of methods will be used to communicate teaching and learning to all parents. Impact: by June 2026 95% of Parents will report improved communication through an online questionnaire. Pupil voice will be encouraged to inform school life and school improvement. Pupils will have opportunity to lead within school empowering confident individuals, effective contributors, successful learners and responsible citizens. Impact: Improved engagement and participation. |  | - Classes will work with clear stretch aim for overall pupil progress and at least 2 specific teaching aims relating to measureable tools for writing skills. - Pupils will be able to discuss their progress, next steps and run charts. - Before and after measurements of pupil engagement will demonstrate an increase in enjoyment of writing. - All classes will engage with development of checklist to improve presentation skills across whole school. - All classes will participate in monthly jotter moderation – self, peer. - All classes will participate in termly jotter moderation by SLT. - Completion of Catch-Up numeracy training by Principal Teacher - Learners identified via XBRA Data as not on track will receive weekly support for Numeracy - Principal Teacher and class teachers will regularly track and monitor progress of identified learners using assess, adapt, abandon approach for interventions. - Class teacher and Principal teacher will develop Strategy Sheet detailing distinct support offered to identified learners not meeting XBRA level expected for stage within Numeracy organiser. - 100% of parents (P1 – P7) will be invited to Learning workshops to highlight teaching and learning within class/stage. - Entry and Exit data will demonstrate at least 95% of attendees report improved knowledge and understanding of taught literacy and numeracy strategies. - 100% of parents of identified learners receiving Numeracy support will be invited to support session. Parental feedback will report raised awareness of how they can support learners with numeracy at home. - By 31st January 2026 a revised school Attendance Policy will be shared with stakeholders. - By 30th June 2026 100% of parents of those children with attendance data falling below 94.5% will have been invited to Attendance Support session within Nurture space. - Surveys collected in September 2025 and June 2026, alongside minutes of SPPG meetings, pupil feedback during assemblies and parent conversations will demonstrate a raised awareness in knowledge and understanding of impact of poor attendance on learning and health & wellbeing. - By October 2025 100% of learners will have a Boxall Profile, Wellbeing Web and GMWP. - Baseline assessments (above) and Attendance Data will be used to timetable Nurture support sessions across Primary. - Weekly nurture sessions will be introduced to Pre-5 to raise awareness of OCTNE journey and support achievement of Priorities 1), 3) and 5) across setting. - Baseline assessments will be gathered in September 2025 from all children, parents and staff to ascertain priorities for supporting young people’s health and wellbeing – eg Sleep Routines, Social Media, Bereavement etc. This feedback will inform series of information workshops for learners and parents delivered in nurture space. - We will measure success via reduction I referrals to SLT for dysregulated behaviour, reduction in PERS100, Class Teacher feedback and Head Teacher tracking & monitoring termly meetings. - Parent Council will engage with community to fundraise for playground re-design and equipment. - Parent Council will apply for community grants to support fundraising efforts for new playground equipment. - Parent Council will work alongside Pupil Council to arrange a diet of fundraising activities. - Feedback gathered at termly events (The Big Question) via exit interviews will demonstrate enhanced understanding of Health & Wellbeing supports, Outdoor Learning and importance of Parental Engagement for learners wellbeing. The following offers will be made to all parents by June 2026: - 1 x Literacy workshop - 1 x Numeracy workshop - 1 x Health & Wellbeing workshop - 1 x Parents Afternoon/Evening - 3 x Celebrations of Learning (Christmas Show, Sports Day, End of Year Celebration) - 3 x Curriculum Flyers - 1 x end of Year Report Via a series of Home Learning tasks we will be able to evidence improved Parental Engagement and understanding for skills and pupil empowerment. At termly workshops parents will feedback enhanced ability to support home learning tasks. School will provide regular communications via Seesaw, Facebook and Twitter. - By May 2026 80% of pupils feel that their voice is heard and that their decisions have an impact on their school life demonstrated by a pupil survey. |  |  | No No Yes No Yes Yes Yes No Yes Yes No |

Note: This section of the Improvement Plan can be made available to all relevant stakeholders to provide an overview of the session’s priorities.

| Operational Improvement Planning (Action Plan) for Establishment: |  |  |  | Session: 2025-2026 |
| --- | --- | --- | --- | --- |
| Strategic Priority 1: | Title: Improving Attainment and Attendance |  |  |  |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. - High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  |  |  |
| National Improvement Framework Priorities | HGIOS 4 | Early Learning and Childcare Quality Indicators |  | Argyll and Bute Education Key Objectives |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/Securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress - Safeguarding and child protection |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |
| Key Actions (How) |  | Lead Person | Timescale | Success Criteria to facilitate evaluation of learners’ progress |
| Attainment - Literacy QI Approach to Improving Writing - Attendance at Argyll and Bute training for cohort 7/8 of QI writing. This involves the following: - 2 in person days - 5 x twilights - 1 x optional twilight - Full implementation of the writing bundle and associated QI measurement tools within selected classrooms. - Feedback and reporting on progress to other members of the cohort. - Observation by L Johnstone of a lesson and associated feedback - Observation and monitoring of progress by school lead, with associated professional discussion - Collation and sharing of data related to impact Professional discussion of approaches to writing pedagogy following completion of the programme. Whole school establishment and understanding of the future role of QI writing. Creation of a plan for future training / development if appropriate. Written Presentation Skills - Analysis of written work as at June 2025 with staff and learners will determine a ‘Gold Standard’ for written work. Learners will complete a WAGOLL by Sept. 2025 to be used as a checklist to ensure progress and improvement for all written tasks. - Learners’ written work will be moderated by self and peers monthly and by SLT termly to provide feedback and ensure progress and improvement. Bookbug Sessions P1 – P4 will work alongside Pre-5 to participate in monthly Bookbug sessions, delivered by Class Teacher and Childcare & Education Worker - Bookbug sessions offered to parents/carers of Pre-5 children at Strachur ELC - Bookbug sessions offered to wider community - Intergenerational Bookbug session offered to wider community - Intergenerational Reading offered across whole establishment Attainment - Numeracy Analysis of XBRA Data, GL Numeracy assessments and SNSA as at June 2025 will identify learners who are not at expected XBRA measures for stage. - Numeracy interventions will be timetabled for identified learners alongside ongoing assessments to identify gaps in learning and plan for next steps. - Principal Teacher to complete Catch-up Numeracy training - Support for Learning paperwork will be created for identified individuals will be shared with parents. Parental Learning workshops will be offered to: - a) all parents once per session and - b) parents of identified learners across session to support with Numeracy interventions and encourage support at home Attendance Monitor weekly attendance reports to ensure children are attending school in line with local authority targets or above. For those learners not meeting criteria: - Directly contact families of learners falling below authority stretch aim of 94.5% - Revisit School Attendance Policy with PT of Health & Wellbeing - Raise awareness of importance of Attendance for all pupils at weekly assembly. - Raise awareness of importance of Attendance to all parents via termly Newsletters - Communicate weekly or monthly attendance data to parents and pupils to raise awareness of schools journey and authority aims. - Schedule Nurture input for those families falling below 94.5% stretch aim to raise awareness of importance of good attendance and provide offers of support to help improve attendance. |  | L Johnstone Principal Teacher Teacher(s) and L Johnstone Teacher(s) L Johnstone Teacher(s) and L Johnstone Head Teacher/Class Teachers SLT/Class Teachers/CCEW Principal Teacher/Class Teachers Principal Teacher/class teachers SLT/Class teachers Head Teacher | Feb – May 2026 for Cohort 8 Following completion of programme June 2025 – June 2026 Sept 2025 – June 2026 Aug 2025 – Aug 2026 Oct 2025 – June 2026 Aug 2025 - June 2026 August 2025 – June 2026 | Each class will have a clear stretch aim for overall pupil progress and at least 2 specific teaching aims relating to measurable tools for writing skills. Every teacher will be implementing the writing bundle in full, including sharing run charts with pupils. Pupils will be able to talk about their progress and next steps both individually and as a class. Practitioners will use a Fishbone tool to analyse the reasons behind continued non-attainment and work with AHPs and other experts to consider ways of further supporting pupils. Before and after measurements of pupil engagement will demonstrate an increase in enjoyment of writing. Staff will report enjoyment of teaching writing. There will be clear evidence of progress towards initial stretch and teaching aims. 90% of children identified for Numeracy support will demonstrate progress. Following Numeracy intervention, 80% of targeted learners will be on track to achieve expected level of attainment by June 2026. 95% of learners will be able to evidence at least 3 pieces of written work which has achieved schools Gold Standard for Written Presentation by June 2026. Baseline data at September 2025 compared against data collected at May 2026 will demonstrate 80% of staff and parents participating reporting improved knowledge and understanding of importance of; - Sharing Books, songs and rhymes daily - Allowing time for cuddling and bonding - Relaxing as a family Staff will report 80% of children taking part demonstrating: - Improved confidence - Improved emotional, cognitive and social development from Week 1 to end of session - Developing love of stories and understanding importance of reading Numeracy interventions will be used to support 100% of learners who are not at expected XBRA Numeracy measure for stage. By June 2026 school ACEL Data for Numeracy will have improved by 5% to 83% in line with authority stretch aim for 2025/26 . 100% of parents of those learners targeted for Numeracy interventions, will be aware of the support offered to their child and discuss Strategy Sheet put in place to record support. 100% of parents (P1 – P7) will be invited to Learning workshops to highlight teaching and learning within class/stage. Entry and Exit data will demonstrate at least 95% of attendees report improved knowledge and understanding of taught literacy and numeracy strategies. 100% of parents of identified learners receiving Numeracy support will be invited to support session. Parental feedback will report raised awareness of how they can support learners with numeracy at home. 80% of learners targeted for support will report parental support with homework following parent support sessions. Whole school XBRA Data for June 2026 for Numeracy will increase by a minimum of 2% and be in line with Stretch Aim of 85%. By 31st May 2026 school attendance data will demonstrate an increase to 94.5% from a baseline (31st May 2025) of 91.25%. By 31st January 2026 a revised school Attendance Policy will be shared with stakeholders. By 30th June 2026 100% of parents of those children with attendance data falling below 94.5% will have been invited to Attendance Support session within Nurture space. Surveys collected in September 2025 and June 2026, alongside minutes of SPPG meetings, pupil feedback during assemblies and parent conversations will demonstrate a raised awareness in knowledge and understanding of impact of poor attendance on learning and health & wellbeing. |

| Operational Improvement Planning (Action Plan) for Establishment: |  |  |  | Session: 2025-2026 |
| --- | --- | --- | --- | --- |
| Strategic Priority 2: | Title: Improving Health & Wellbeing |  |  |  |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. - High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  |  |  |
| National Improvement Framework Priorities | HGIOS 4 and Early Learning and Childcare Indicators | Early Learning and Childcare Quality Indicators |  | Argyll and Bute Education Key Objectives |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/Securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress Safeguarding and child protection |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |
| Key Actions (How) |  | Lead Person | Timescale | Success Criteria to facilitate evaluation of learners’ progress |
| Our Children, Their Nurturing Education (OCTNE) Data A range of data will be gathered from August 2025 to support targeted, weekly Nurture sessions for identified learners and their families. This will include Boxall Profiling for all children and Wellbeing Webs completed termly for all learners and Glasgow Motivation & Wellbeing Profile (GMWP). - Class Teacher (Heather Cassidy) will complete Boxall Profiling training by Sept 2025 - Head Teacher will complete GMWP for all children by Oct 2025 - Head Teacher will complete Seasons for Growth training to support targeted families by Oct 2025 - Baseline assessments (above) and Attendance Data will be used to timetable Nurture support sessions across Primary. - Weekly nurture sessions will be introduced to Pre-5 to raise awareness of OCTNE journey and support achievement of Priorities 1), 3) and 5) across setting. - Baseline assessments will be gathered in September 2025 from all children, parents and staff to ascertain priorities for supporting young people’s health and wellbeing – eg Sleep Routines, Social Media, Bereavement etc. This feedback will inform series of information workshops for learners and parents delivered in nurture space. |  | Head Teacher Head Teacher Head Teacher Head Teacher Head Teacher | August 2025 – June 2026 Aug 2025 Oct 2025 Sept 2025 Jan 2026 Jan 2026 Sept 2025 | By October 2025 100% of learners will have a Boxall Profile, Wellbeing Web and GMWP. By Oct 2025 all families will be offered Seasons for Growth input. By Jan 2026 100% families of learners whose attendance is below 94.5% will be offered Nurture support for attendance By Jan 2026 100% of families of Pre-5 learners will be offered Nurture input. By Sept 2025 all learners and their families will be consulted on how we can support Health 7 Wellbeing with information sessions. We will subsequently use feedback to deliver information sessions open to all parents. 90% of parents attending information sessions for Health 7 Wellbeing will report enhanced knowledge, understanding and ability to support their child with identified Health & Wellbeing issues. |

| Operational Improvement Planning (Action Plan) for Establishment: |  |  |  |  | Session: 2025-2026 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Priority 3: | Title: Improve Parental Engagement and Pupil Empowerment |  |  |  |  |  |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. - High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  |  |  |  |  |
| National Improvement Framework Priorities | HGIOS 4 | Early Learning and Childcare Quality Indicators |  |  | Argyll and Bute Education Key Objectives |  |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/Securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress Safeguarding and child protection |  |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |  |
| Key Actions (How) |  | Lead Person |  | Timescale | Success Criteria to facilitate evaluation of learners’ progress |  |
| Parental Engagement Improving Outdoor Spaces for Primary & Pre-5 Learners - Parent Council will engage with community to fundraise for playground re-design and equipment. - Parent Council will apply for community grants to support fundraising efforts for new playground equipment. - Parent Council will work alongside Pupil Council to arrange a diet of fundraising activities. Parental Literacy, Numeracy and Health & Wellbeing Focus workshops A clear calendar of Parental Engagement offers for all classes (inc Pre-5) across the academic year will be shared via Aug – Oct Newsletter to include: - 1 x Literacy workshop - 1 x Numeracy workshop - 1 x Health & Wellbeing workshop - 1 x Parents Afternoon/Evening - 3 x Celebrations of Learning (Christmas Show, Sports Day, End of Year Celebration) - 3 x Curriculum Flyers - 1 x end of Year Report - Pre-5 to P1 Induction Programme Social Media Following success of Seesaw introduction this session, we will encourage Parent Council and wider Parent body to engage with school’s newly formed Twitter and Facebook accounts to widen community knowledge and understanding of school events etc. Pupil Empowerment - Pupil Council will work with Parent Council to design plan for new playground and outdoor equipment. - Pupil Council will engage with Parent Council to develop fundraising ideas to fund plan for new playground equipment, including community engagement. - Pupil Council will lead wider Pupil body to examine Charities and decide on a Charity they wish to represent and fundraise for over session 2025 – 2026, raising awareness of finances, teamwork, project management and causes that affect our communities and wider world. |  | Chair of Parent Council/SLT Head Teacher Heather Cassidy Principal Teacher Parent Council/Principal Teacher Principal Teacher |  | Aug 2025 – June 2026 Aug 2025 – June 2026 Sept 2025 – June 2026 Aug 2025 – June 2026 | By June 2026 outdoor spaces across Strachur Primary and Pre-5 will have at least one improvement in form of decoration and installation of new equipment. By June 2026 100% of parents will have been invited to participate in Literacy, Numeracy and Health & Wellbeing workshops. By June 2026 100% of parents will have been invited to join 3 Celebrations of Learning. By June 2026 100% of parents will have been sent 3 x Curriculum Bulletins and one end of year report. By June 2026 we will have gathered attendance data for all above school events and be able to work on improving attendance with parental feedback following events as part of our ongoing improvement journey. By June 2026 at least 75% of Parents will have engaged with school’s Facebook and/or Twitter accounts. By June 2026 Parent Council will have shared at least 5 pieces of information to update school community on their ongoing work to support improving school and Pre-5 outdoor spaces. |  |
| Operational Improvement Planning (Action Plan) for Establishment: |  |  |  |  | Session: 2025-2026 |  |
| Strategic Priority ELC: | Title: Developing Partnership working with Pre-5, School and Parents |  |  |  |  |  |
| National Improvement Framework Key Outcomes - A globally respected and accountable education system that empowers learners with the skills and knowledge to succeed. - Strong partnerships between schools, early years settings, families, and wider services to support young people. - An inclusive and relevant curriculum that equips learners for society and a sustainable future. High achievement for all, with targeted action to close the poverty-related attainment gap. - Skilled teachers and leaders delivering excellent learning, especially for those with additional support needs. - Positive relationships, improved attendance, and a culture of dignity, respect, and engagement. - Effective use of digital technology to enhance learning, teaching, and equity. |  |  | National Standard |  |  |  |
|  |  |  | - Staffing, leadership and management - Development of children’s cognitive skills, health and wellbeing - Physical environment - Self-evaluation and improvement |  |  | - Parent and carer engagement - Inclusion - Business sustainability - Fair work - Payment process - Food |
| National Improvement Framework Priorities | HGIOS 4 | Early Learning and Childcare Quality Indicators |  |  | Argyll and Bute Education Key Objectives |  |
| - Placing the human rights and needs of every child and young person at the centre of education. - Improvement in children and young people’s health and wellbeing. - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | 1.1 Self-evaluation for self-improvement 1.2 Leadership for learning 1.3 Leadership of change 1.4 Leadership and management of staff 1.5 Management of resources to promote equity 2.1 Safeguarding and child protection 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 2.5 Family learning 2.6 Transitions 2.7 Partnership 3.1 Ensuring wellbeing, equality and inclusion 3.2 Raising attainment and achievement/Securing children's progress 3.3 Increasing creativity and employability/ Developing creativity and skills for life and learning | Leadership - Leadership and management of staff and resources - Staff skills, knowledge, values and deployment - Leadership of continuous improvement Children thrive and develop in quality spaces - Children experience high quality spaces Children play and learn - Play and learning - Curriculum - Learning, teaching and assessment Children are supported to achieve - Nurturing care and support - Wellbeing inclusion and equality - Children’s progress Safeguarding and child protection |  |  | - Best start for learners - Ambitious learners - Nurtured learners - Connected learners - Lifelong learners |  |
| Key Actions (How) |  | Lead Person |  | Timescale | Success Criteria to facilitate evaluation of learners’ progress |  |
| Literacy, Numeracy and Health & Wellbeing - Parental Literacy, Numeracy and Health & Wellbeing Focus workshops A clear calendar of Parental Engagement offers will be made available across the academic year and shared with Pre-5 parents via Aug – Oct Newsletter. Pre-5 CCEWs will be supported by Principal Teacher to enhance Stay & Play sessions with enriched literacy and numeracy experiences within nursery environment. Bookbug Sessions Pre-5 to participate in monthly Bookbug sessions, delivered by Childcare & Education Worker and in partnership with newly appointed Provisionally Registered Teacher - Bookbug sessions offered to parents/carers of Pre-5 children at Strachur ELC - Bookbug sessions offered to wider community - Intergenerational Bookbug session offered to wider community - Intergenerational Reading offered across whole establishment Our Children, Their Nurturing Education (OCTNE) - Weekly nurture sessions will be introduced to Pre-5 to raise awareness of OCTNE journey and support achievement of Priorities 1), 3) and 5) across setting. Parental Engagement Improving Outdoor Spaces for Pre-5 Learners - Parent Council will engage with community to fundraise for playground re-design and equipment. - Parent Council will apply for community grants to support fundraising efforts for new playground equipment. - Parent Council will work alongside Pupil Council (including Pre-5 representation) to arrange a diet of fundraising activities. |  | Head Teacher/Principal Teacher SLT/Pre-5 Staff Head Teacher Chair of Parent Council/SLT |  | Aug 2025 – Aug 2026 Aug 2025 – Aug 2026 Jan 2026 – June 2026 Aug 2025 – June 2026 | By June 2026 100% of parents will have been invited to participate in Literacy, Numeracy and Health & Wellbeing workshops. Baseline data at September 2025 compared against data collected at May 2026 will demonstrate 80% of staff and parents participating reporting improved knowledge and understanding of importance of; - Sharing Books, songs and rhymes daily - Allowing time for cuddling and bonding - Relaxing as a family Staff will report 80% of children taking part demonstrating: - Improved confidence - Improved emotional, cognitive and social development from Week 1 to end of session - Developing love of stories and understanding importance of reading By Jan 2026 100% of families of Pre-5 learners will be offered Nurture input. By June 2026 outdoor spaces across Strachur Primary and Pre-5 will have at least one improvement in form of decoration and installation of new equipment. |  |

| Pupil Equity Funding ¦ Planning and Reporting | School Name: Strachur Primary School |
| --- | --- |
| - Strachur Primary School is a small, non-denominational school in the village of Strachur lying on the shores of Loch Fyne. The school has a large, far-reaching, rural catchment with many children travelling to school by bus. The school roll will be 27 as of August 2025 in two composite classes. All children live within SIMD 5 – 6 and and of current roll, 30% are in receipt of FSM. With these small numbers, the school has a focus on raising attainment for all (equity) rather than comparing SIMD 1-2 with 3-10. - Examination of school roll against ACEL data, attendance data and local professional knowledge of the six family priority types (lone parent, minority ethnic, families with disabled adult or child, young mothers (under 25), families with child under one, larger families (3+ children) has identified 7 learners (30%) for next sessions cohort who re a) not on track to meet expected levels across one or more organisers for CfE and who meet criteria of six family priority types and/or attendance rate falls below 94%. - These learners will be targeted with interventions to support improved attendance, raising attainment in literacy and numeracy with specific measures alongside drive to improve whole school attainment in these organisers. Baseline assessments (ACEL achievement, standardised assessments and school tracking information) will be compared against end of session data to ascertain percentage increases. - We have examined a range of data to identify a cohort of learners to be supported via PEF. This has included SIMD, FSM, 6 priority types. We have compared this information against ACEL data and Attendance to identify targeted individuals. To support the anonymity of learners this report will discuss ‘whole school attainment’. However, at school level, specific measures are in place to identify, support and track those learners meeting priority types. |  |

| Pupil Equity Funding ¦ Planning and Reporting |  |  |  |  |
| --- | --- | --- | --- | --- |
| Where does the gap exist? - Use data to consider current filter cohorts – SIMD, FSM, Gender, ASN, Service families - Use data to reflect on local / contextual knowledge / 6 priority family types - Who is your target group? - Detail the relevant organiser from: - Attainment and Achievement - Attendance - Inclusion - Engagement - Participation - What are the specific barriers to learning? | What difference do you want to see and how will you know? (what, when and how)? - Aim and expected outcome of intervention / support – be as specific as you can, using data to set targets - How will you know your interventions are having an impact/improving outcomes? - Proposals for measuring impact (including specific reference to targeting young people most affected by poverty). - Data, existing (baselines) and new (gathered through course of timescale), which will be required. - Include plans for when / how data will be collected and reported. |  | What are you planning to do with your PEF Allocation? - Proposals to address identified issues within Literacy, Numeracy and/or Health and Wellbeing. - Plans to work in partnership with other schools/local partners/providers, if applicable | What was the impact of your planned interventions? - Do you have quantitative and qualitative data that tells the story of attainment and achievement for the target group(s)? - What was the impact for pupils based on the outcome(s)/measures(s) you identified? |
| Gap Identified Detail gap that has been identified through data scrutiny | Outcome(s) This is what we want to happen for the targeted pupils – the change we want to see - what, for whom, by how much, by when? | Measure(s) This is the data we will use to determine whether or not the outcome has been met | Key Actions/Activities The actions we are planning in order to improve outcomes in the areas we have identified for the target group(s) experiencing disadvantage due to poverty. Include detail key/lead staff for actions/activities. | Mid Year Impact (To be completed in February) This is where we check to see if things are on track and if we need to continue, adapt or abandon what we had planned. Use tracking data to evidence impact thus far and detail any changes. What is progress looking like based on your planned outcome/measure action/ – on track, complete, not on track? |
| Attendance Whole school attendance data has been examined alongside FM, SIMD, 6 priority family types and ACEL data. We can see a correlation between learners within 6 priority type who are not meeting expected levels attendance falling below 94%. | 86% (6 out of 7) of targeted learners will demonstrate a 5%+ improvement in attendance data by June 2026 as compared to June 2025 data. | Seemis attendance data | Attendance Head Teacher to monitor weekly attendance reports to ensure children are attending school in line with local authority targets or above. For those identified learners not meeting criteria - Directly contact families of learners falling below authority stretch aim of 94.5% - Raise awareness of importance of Attendance for all pupils at weekly assembly. - Raise awareness of importance of Attendance to all parents via termly Newsletters - Raise awareness of importance of Attendance to all parents via Health & Wellbeing Parental Learning workshop - Communicate weekly or monthly attendance data to parents of targeted learners to raise awareness of impact on child. - Schedule Nurture input for those families falling below 94.5% stretch aim to raise awareness of importance of good attendance and provide offers of support to help improve attendance. Whole school attendance data will improve from 80% (avg. June 2025) to minimum of 90% by June 2026. |  |
| Attainment - Numeracy Analysis of XBRA Data, GL Numeracy assessments and SNSA as at June 2025 is used to identify learners within PEF cohort who are not at expected XBRA measures for stage. Daily Mental maths challenges to continue across P3 – P7. | Whole school XBRA Data for June 2026 for Numeracy will increase by a minimum of 2% and be in line with Stretch Aim of 85%. 100% of identified learners (4) will receive numeracy interventions of Catch-up Numeracy at least twice per week. 75% of identified learners (3) will demonstrate improvement in pre and post Numeracy intervention baseline assessments. 100% of parents of those learners targeted for Numeracy interventions, will be aware of the support offered to their child and discuss Strategy Sheet put in place to record support. 100% of parents of identified learners receiving Numeracy support will be invited to support session. Parental feedback will report raised awareness of how they can support learners with numeracy at home. 100% of parents of identified learners receiving Numeracy support will be invited to support session. Parental feedback will report raised awareness of how they can support learners with numeracy at home. Entry and Exit data will demonstrate at least 95% of attendees report improved knowledge and understanding of taught literacy and numeracy strategies. 75% (3) of learners targeted for support will report parental support with homework following parent support sessions. Almost all learners will demonstrate improved mental ability in Maths via Pre/Post mental maths testing (Prim-Ed, GL Assessments) by June 2026 compared to baseline results for June 2025. | ACEL Numeracy Data 2026 Numeracy Intervention timetable for Principal Teacher Baseline Numeracy Assessment Post Numeracy Intervention assessment Pupil Strategy sheets Parent meeting data Entry/Exit slips Meeting attendance records Parental feedback Entry/Exit data Pupil feedback Parental feedback Mental Maths tests | - Numeracy interventions will be timetabled for identified learners alongside ongoing assessments to identify gaps in learning and plan for next steps. - Principal Teacher to complete Catch-up Numeracy training and deliver 2-3 weekly numeracy attainment sessions to identified learners - Support for learning paperwork (Pupil strategy sheets) will be created for identified individuals and shared with parents to promote and support learning at home. - Parental Numeracy learning workshops will be offered to: a) all parents once per session and b) parents of identified learners across session to support with Numeracy interventions and encourage support at home |  |
| Attainment - Literacy Analysis of XBRA Data, Star reading scores and SNSA as at June 2025 is used to identify learners within PEF cohort who are not at expected XBRA measures for stage. Renew subscription of Picture News to continue improvement journey for Listening & Talking | Whole school XBRA Data for June 2026 for Reading will increase by a minimum of 2% and be in line with Stretch Aim of 76%. 100% of identified learners (4) will receive literacy interventions (Catch-up Literacy, 5 Min Literacy box, Accelerated Reader, Toe by Toe) at least twice per week. 75% of identified learners (3) will demonstrate improvement in pre and post Literacy intervention baseline assessments. 100% of parents of those learners targeted for Literacy interventions, will be aware of the support offered to their child and discuss Strategy Sheet put in place to record support. 100% of parents of identified learners receiving Literacy support will be invited to support session. Parental feedback will report raised awareness of how they can support learners with Literacy at home. Entry and Exit data will demonstrate at least 95% of attendees report improved knowledge and understanding of taught literacy strategies. 75% (3) of learners targeted for support will report parental support with homework following parent support sessions. Whole school data for Listening & Talking will improve by 3% by June 2026. | ACEL Data for Reading for June 2026 Literacy Intervention timetables ACEL Data Pupil strategy sheets Parental feedback Meeting attendance records Parental feedback Entry/Exit Data Pupil feedback Improved homework ACEL Data Listening & Talking June 2026 | - Literacy interventions will be timetabled for identified learners alongside ongoing assessments to identify gaps in learning and plan for next steps. - ASN trained to deliver Catch-Up Literacy will be funded via PEF to deliver 2-3 weekly attainment sessions to identified learners - Support for learning paperwork (Pupil strategy sheets) will be created for identified individuals and shared with parents to promote and support learning at home. - Parental Literacy learning workshops will be offered to: a) all parents once per session and b) parents of identified learners across session to support with Literacy interventions and encourage support at home Timetable weekly Listening & Talking sessions across whole school |  |
| Improving Health & Wellbeing - Parental Learning Workshops A clear calendar of Parental Engagement offers for all classes (inc Pre-5) across the academic year will be shared via Aug – Oct Newsletter. Nurture room will be timetabled to offer support and strategies to learners identified with barriers to learning. Parent & Pupil Health & Wellbeing questionnaires will be used to inform and develop series of workshops to support Children’s mental health priorities – eg Sleep /routines, Social Media, Bereavement etc. | By June 2026 100% of parents will have been invited to participate in Literacy, Numeracy and Health & Wellbeing workshops. By June 2026 100% of parents of those learners identified to receive Literacy and/or Numeracy support for learning will have attended 1:1 mtg. to discuss the individualised support offered to their child. 100% of parents of those learners targeted for PEF Attendance and/or Literacy and/or Numeracy interventions, will be aware of the support offered to their child and discuss Pupil Strategy Sheet put in place to record support. 100% of parents attending Attendance support session will report raised awareness across wider parent body of importance of school attendance. 80% of identified learners receiving Nurture input will demonstrate improvement of 1 – 2 areas of pre/post assessments. 100% of learners attending information sessions for social, emotional and mental health will report improved awareness of how to support mental health | Parental Workshop attendance data Meeting attendance data Pupil Strategy sheets Meeting data Meeting data Nurture room timetable Boxall Profiles Wellbeing Webs GMWP Timetables for support sessions Entry/Exit Questionnaires | - Plan Nurture input for those families with attendance falling below 94.5% stretch aim to raise awareness of importance of good attendance and provide offers of support to help improve attendance. - Engage support from PT Health & wellbeing to inform Parent raised awareness of attendance matters. - Plan Literacy and Numeracy Parental Learning workshops for all parents to support home learning and raise awareness of taught strategies. - Plan support meetings for parents of those learners targeted for PEF Numeracy and Literacy interventions to share Pupil Strategy sheets so that they are aware of the individualised support offered to their child and how they can support at home. - Nurture room timetabled with teacher and support for 1 – 2 sessions weekly - Conduct whole school Boxall Profiling, Wellbeing Webs and GMWP - Discuss assessments with Pupil, Teacher, Parent - Research resources & strategies to support identified learners to overcome barriers to learning - Conduct pupil questionnaires for at August 2025 - Conduct Parental questionnaires for at August 2025 - Prioritise pupil learning workshops from above data - Conduct Pre and Post workshops data - Pupils to feedback learning to parents at end of sessions by either Presentation, Newsletter or Online information |  |
| Parental Engagement - Social Media A range of methods will be used to communicate teaching and learning to all parents. | By June 2026 95% of Parents will report improved communication through an online questionnaire. | Social Media platform statistics | School to provide regular communications via Seesaw, Facebook and Twitter (at least 2 per week on at least one platform). |  |

| Pupil Equity Funding ¦ Planning and Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Staff Spend Details * Note: - Please see information from HR regarding PEF posts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  | Post |  |  | Start Date |  |  |  | Proposed End Date |  |  |  | Cumulative Time in Post |  |  |  |
| Catriona Wilson |  |  | ASN (2.5 hours) |  |  | 12/08/2024 |  |  |  | 02/04/26 |  |  |  | 20 months |  |  |  |
| Highlight the Intervention for Equity addressed by your PEF interventions/projects https://education.gov.scot/improvement/self-evaluation/Interventions%20for%20Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Early intervention and prevention |  | Social and Emotional Wellbeing |  |  | Promoting Healthy Lifestyles |  |  |  | Targeted approaches to Literacy and Numeracy |  |  | Promoting a High Quality Learning Experience |  |  |  | Differentiated Support |  |
| Employability and Skills Development |  | Engaging Beyond the School |  |  | Partnership Working |  |  |  | Professional Learning and Leadership |  |  | Research and Evaluation to Monitor Impact |  |  |  | Using Evidence and Data |  |
| Spend Details |  |  |  |  |  |  | Carry Forward 2024 - 2025 |  |  |  |  |  | PEF Allocation 2025 - 2026 |  |  |  |  |
| Staffing £1600 Supported Study Resources 1877.79 Purchased/Commissioned Services Other |  |  |  |  |  |  | £ 755 |  |  |  |  |  | £ 3103 |  |  |  |  |
|  |  |  |  |  |  |  | Mid-Year Spend checkpoint (Dec-Jan) Identify any significant changes in expenditure. |  |  |  |  |  | Final spend (End of Session) Identify any significant changes in expenditure. |  |  |  |  |
|  |  |  |  |  |  |  | £ |  |  |  |  |  | £ |  |  |  |  |